## Slide 1
Weekly Action Tracker Review
Strategic initiatives and governance actions | Week ending 01 Oct 2026

## Slide 2
24% of actions are complete; 5 are overdue
Source: Action Tracker, as of 01 Oct 2026
21
Total actions
5
Completed
10
In progress
2
Blocked
5
Overdue
• Overdue actions are concentrated in Technology (2 of 5); consider a focused follow-up.
• 2 action(s) are blocked and need escalation or a management decision.
• 6 action(s) fall due in the next 7 days.
• Open actions are on average 40% complete.
Key messages

## Slide 3
Progress by status and by function
Source: Action Tracker, as of 01 Oct 2026
Chart: Actions by status
| Not Started | In Progress | Blocked | Completed
Actions | 4 | 10 | 2 | 5
Chart: Actions by function and RAG status
| Business | Compliance | Finance | Infrastructure | Operations | Risk | Technology
Done | 0 | 2 | 2 | 0 | 1 | 0 | 0
On track | 3 | 0 | 1 | 0 | 1 | 1 | 1
Amber | 1 | 0 | 0 | 1 | 0 | 0 | 2
Red | 0 | 1 | 0 | 0 | 1 | 1 | 2

## Slide 4
5 overdue and 2 blocked actions need attention
Source: Action Tracker, as of 01 Oct 2026
ID | Action Item | Owner | Function | Priority | Due | Issue
A-012 | Close access-review findings | Sana Qureshi | Risk | High | 17 Sep | Overdue 14d
A-003 | Compliance review of digital consent flow | Rohan Das | Compliance | High | 25 Sep | Overdue 6d + blocked
A-002 | Sign off UAT test scripts | Neha Iyer | Technology | High | 27 Sep | Overdue 4d
A-011 | Security assessment of shortlisted vendors | Ishaan Verma | Infrastructure | High | 06 Oct | Blocked
A-008 | Identify vendor contract savings | Vikram Rao | Operations | Medium | 29 Sep | Overdue 2d
A-021 | Automate reminder emails for open actions | Kunal Shah | Technology | Medium | 30 Sep | Overdue 1d

## Slide 5
6 actions fall due in the next 7 days: follow-ups required
Source: Action Tracker, as of 01 Oct 2026
ID | Action Item | Owner | Function | Due | Progress | Status
A-019 | Build prototype dashboard | Ishaan Verma | Technology | 02 Oct | 45% | In Progress
A-004 | Reconcile data fields to regulatory template | Priya Nair | Finance | 04 Oct | 60% | In Progress
A-014 | Compile evidence pack for internal audit | Neha Iyer | Technology | 05 Oct | 40% | In Progress
A-011 | Security assessment of shortlisted vendors | Ishaan Verma | Infrastructure | 06 Oct | 20% | Blocked
A-009 | Present savings options to steering committee | Aarav Mehta | Business | 07 Oct | 0% | Not Started
A-016 | Set up outreach tracker for client documents | Kavya Reddy | Business | 08 Oct | 65% | In Progress