## Tracker
ID | Initiative | Action Item | Owner | Function | Priority | Status | Start Date | Due Date | % Complete | Last Update | Remarks | Days to Due | RAG
A-001 | Client Onboarding Digitisation | Finalise process map for e-onboarding | Aarav Mehta | Operations | High | Completed | 2026-08-22 | 2026-09-21 | 100% | 2026-09-21
A-002 | Client Onboarding Digitisation | Sign off UAT test scripts | Neha Iyer | Technology | High | In Progress | 2026-09-11 | 2026-09-27 | 70% | 2026-09-29 | Two test cases pending
A-003 | Client Onboarding Digitisation | Compliance review of digital consent flow | Rohan Das | Compliance | High | Blocked | 2026-09-06 | 2026-09-25 | 40% | 2026-09-22 | Awaiting legal opinion
A-004 | Regulatory Reporting Automation | Reconcile data fields to regulatory template | Priya Nair | Finance | High | In Progress | 2026-09-16 | 2026-10-04 | 60% | 2026-09-30
A-005 | Regulatory Reporting Automation | Automate monthly return generation | Kunal Shah | Technology | Medium | In Progress | 2026-09-21 | 2026-10-13 | 30% | 2026-09-28
A-006 | Regulatory Reporting Automation | Document control framework for reports | Sana Qureshi | Risk | Medium | Not Started | 2026-10-01 | 2026-10-21 | 0% | 2026-09-26
A-007 | Cost Optimisation FY27 | Baseline cost per transaction by product | Meera Pillai | Finance | High | Completed | 2026-09-01 | 2026-09-26 | 100% | 2026-09-26
A-008 | Cost Optimisation FY27 | Identify vendor contract savings | Vikram Rao | Operations | Medium | In Progress | 2026-09-19 | 2026-09-29 | 50% | 2026-09-27 | Two contracts still under review
A-009 | Cost Optimisation FY27 | Present savings options to steering committee | Aarav Mehta | Business | High | Not Started | 2026-10-03 | 2026-10-07 | 0% | 2026-09-29
A-010 | Vendor Consolidation | Shortlist vendors via RFP scoring | Vikram Rao | Operations | Medium | In Progress | 2026-09-13 | 2026-10-10 | 55% | 2026-09-29
A-011 | Vendor Consolidation | Security assessment of shortlisted vendors | Ishaan Verma | Infrastructure | High | Blocked | 2026-09-23 | 2026-10-06 | 20% | 2026-09-25 | Vendor has not shared SOC 2 report
A-012 | Audit Findings Remediation | Close access-review findings | Sana Qureshi | Risk | High | In Progress | 2026-08-27 | 2026-09-17 | 80% | 2026-09-28 | Evidence for 3 findings outstanding
A-013 | Audit Findings Remediation | Update policy documents | Rohan Das | Compliance | Medium | Completed | 2026-09-03 | 2026-09-24 | 100% | 2026-09-24
A-014 | Audit Findings Remediation | Compile evidence pack for internal audit | Neha Iyer | Technology | Medium | In Progress | 2026-09-26 | 2026-10-05 | 40% | 2026-09-30
A-015 | KYC Refresh Programme | Prioritise high-risk client segment list | Priya Nair | Compliance | High | Completed | 2026-09-09 | 2026-09-28 | 100% | 2026-09-28
A-016 | KYC Refresh Programme | Set up outreach tracker for client documents | Kavya Reddy | Business | Medium | In Progress | 2026-09-17 | 2026-10-08 | 65% | 2026-09-30
A-017 | KYC Refresh Programme | Define escalation protocol for non-responsive clients | Kavya Reddy | Business | Low | Not Started | 2026-10-04 | 2026-10-26 | 0% | 2026-09-27
A-018 | Productivity Dashboard Rollout | Define KPI dictionary | Meera Pillai | Finance | High | Completed | 2026-09-11 | 2026-09-23 | 100% | 2026-09-23
A-019 | Productivity Dashboard Rollout | Build prototype dashboard | Ishaan Verma | Technology | Medium | In Progress | 2026-09-24 | 2026-10-02 | 45% | 2026-09-30
A-020 | Productivity Dashboard Rollout | Run stakeholder training sessions | Aarav Mehta | Business | Low | Not Started | 2026-10-06 | 2026-10-31 | 0% | 2026-09-29
A-021 | Productivity Dashboard Rollout | Automate reminder emails for open actions | Kunal Shah | Technology | Medium | In Progress | 2026-09-22 | 2026-09-30 | 90% | 2026-09-30
Formulas:
Days to Due = IF([Status]="Completed","",[Due Date]-TODAY())
RAG = IF([Status]="Completed","Done",IF([Due Date]<TODAY(),"Red",IF(OR([Status]="Blocked",AND([Due Date]-TODAY()<=7,J2<0.5)),"Amber","Green")))

## Instructions
How to use this tracker
1. The rows on the Tracker sheet are SAMPLE data. Replace them with your own actions.
2. Type only in columns A to L (blue text). Columns M and N are formulas - do not overwrite.
3. Status must be one of: Not Started, In Progress, Blocked, Completed (dropdown provided).
4. % Complete is entered as a percentage (e.g. 60%). Dates use dd-mmm-yyyy.
5. Run: python report.py --input data/action_tracker.xlsx to generate the weekly deck and follow-up emails.
RAG rules (same logic in Excel and in report.py)
Done : Status = Completed
Red : not completed and Due Date is before today
Amber : Status = Blocked, OR due within 7 days with under 50% complete
Green : everything else