## Slide 1
Weekly Action Tracker Review
Strategic initiatives and governance actions | Week ending 09 Sep 2026

## Slide 2
24% of actions are complete; 0 are overdue
Source: Action Tracker, as of 09 Sep 2026
21
Total actions
5
Completed
10
In progress
2
Blocked
0
Overdue
• 2 action(s) are blocked and need escalation or a management decision.
• 0 action(s) fall due in the next 7 days.
• Open actions are on average 40% complete.
Key messages

## Slide 3
Progress by status and by function
Source: Action Tracker, as of 09 Sep 2026
Chart: Actions by status
| Not Started | In Progress | Blocked | Completed
Actions | 4 | 10 | 2 | 5
Chart: Actions by function and RAG status
| Business | Compliance | Finance | Infrastructure | Operations | Risk | Technology
Done | 0 | 2 | 2 | 0 | 1 | 0 | 0
On track | 4 | 0 | 1 | 0 | 2 | 2 | 5
Amber | 0 | 1 | 0 | 1 | 0 | 0 | 0
Red | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 4
0 overdue and 2 blocked actions need attention
Source: Action Tracker, as of 09 Sep 2026
ID | Action Item | Owner | Function | Priority | Due | Issue
A-003 | Compliance review of digital consent flow | Rohan Das | Compliance | High | 25 Sep | Blocked
A-011 | Security assessment of shortlisted vendors | Ishaan Verma | Infrastructure | High | 06 Oct | Blocked

## Slide 5
0 actions fall due in the next 7 days: follow-ups required
Source: Action Tracker, as of 09 Sep 2026
Nothing due in the next 7 days.